BOUND PROTOCOL

RWA Migration — Milestone Roadmap

Built on deployed APSS infrastructure (BLD stablecoin + liquidity pool)

Non-Technical Stakeholder Edition

12 Milestones · 3 Phases · 22–25 Weeks · $320,000 Development Budget

CONFIDENTIAL · INTERNAL USE ONLY

# Starting Point: What's Already Built

BOUND is not starting from zero. The APSS system — BLD stablecoin and core liquidity pool — is already deployed and operational. This roadmap extends that foundation to support Real-World Asset instant liquidity, rather than building a new protocol from scratch.

| Asset | Status |
| --- | --- |
| APSS System | BLD stablecoin and liquidity pool — deployed and operational |
| BLD Token | Existing stablecoin infrastructure retained as settlement asset |
| Liquidity Pool | Core pool deployed; requires RWA instant-exit extensions |

# Executive Summary

This roadmap presents twelve milestones across three phases, taking BOUND from a locked architecture decision through to live RWA markets on mainnet. Each milestone is written for a non-technical audience: what gets built, what becomes possible as a result, and why it matters strategically.

Development is budgeted at a fixed $320,000 across 22 weeks of engineering execution, with a realistic delivery window of 22–25 weeks to mainnet inclusive of audit and launch buffer. External audit and security competition fees are budgeted and tracked separately from the development allocation.

# Timeline at a Glance

| Phase | Weeks | Scope |
| --- | --- | --- |
| Phase 1: Foundation | Weeks 1–6 | APSS baseline mapped, RWA architecture locked, core contracts aligned, platform ready |
| Phase 2: Build | Weeks 7–16 | Oracle automation, instant exit UX, issuer platform, APIs, pre-audit hardening |
| Phase 3: Audit & Launch | Weeks 17–25 | External audit, public competition, production readiness, RWA mainnet launch |

# Milestones

## Phase 1: Foundation   Weeks 1–6

### M1 · Wks 1–2  —  RWA Architecture Blueprint Locked

The RWA migration specification is finalised. Existing APSS contracts are mapped against target architecture; net-new modules are fully specified with no open design decisions.

- APSS baseline documented — current BLD stablecoin and liquidity pool behaviour catalogued and mapped

- RWA eligibility framework defined — qualifying asset classes, onboarding criteria, and collateral rules

- Haircut model specified — instant-exit pricing logic, parameter bounds, and oracle dependencies

- Migration path agreed — upgrade strategy for APSS contracts without disrupting live BLD markets

- Governance and delivery cadence live — decision log, weekly syncs, escalation path

Strategic outcome:  Engineering proceeds against a locked target state. The pivot is explicit; rework is minimised.

### M2 · Wks 3–4  —  Core Contracts Aligned to RWA Architecture

APSS contracts are extended and new RWA modules are implemented. BLD and the liquidity pool are refactored for RWA instant exits; registry and governance modules are built and unit-tested.

- BLD token aligned — stablecoin accounting extended for RWA collateral and settlement flows

- Liquidity pool extended — instant-exit swap path, reserve tracking, background settlement queue

- RWA registry contract built — onboarding, eligibility enforcement, haircut assignment on-chain

- Governance module extended — proposals, timelock, emergency pause integrated with RWA permissions

- Admin controls scoped — multi-sig emergency levers only; routine operations permissionless

Strategic outcome:  The deployed APSS foundation is preserved while the full RWA stack is assembled around it.

### M3 · Wks 5–6  —  Infrastructure & Platform Readiness

Cloud infrastructure, CI/CD, and application platform are extended for RWA workloads. Teams ship against the new architecture without provisioning debt.

- Environment parity — dev, staging, and testnet reproducible; APSS and RWA stacks deployable on demand

- CI/CD pipeline extended — contract migration tests, integration gates, and safe deployment automation

- Design system and app shell updated — RWA flows, issuer surfaces, and protocol branding consistent

- Observability baseline — logging, metrics, and alerting wired for BLD reserve and pool health

- SEO and metadata foundations — search and social previews reflect RWA positioning

Strategic outcome:  Phase 2 begins with operational infrastructure, not setup. The pivot ships on a proven platform.

## Phase 2: Build   Weeks 7–16

### M4 · Wks 7–9  —  Oracle Engine Operational

The automated pricing and settlement layer is live. BOUND receives real-time RWA valuations and executes haircut and settlement logic without manual intervention.

- Real-time NAV feeds connected — live pricing for all listed RWAs with freshness guards

- Haircut engine automated — discount rates update from oracle data without manual intervention

- Background settlement processor running — queued redemptions execute autonomously

- Failover and redundancy validated — oracle continuity through RPC outages and stale feeds

- Issuer obligation tracker active — missed reporting deadlines flagged and suspension workflows triggered

Strategic outcome:  RWA markets price and settle programmatically. The protocol no longer depends on manual operations.

### M5 · Wks 10–11  —  Instant Exit Swap Live on Testnet

End-to-end RWA-to-BLD instant exit is demonstrable on testnet. Existing BLD liquidity supports the new swap path.

- Instant exit interface complete — asset selection, haircut preview, and execution against extended pool

- Wallet connectivity verified — MetaMask, WalletConnect, and hardware wallet flows production-ready

- Settlement status tracking live — holders follow background redemption progress in real time

- Error handling standardised — failure modes surface clear, actionable messages

- Integration tests passing — APSS pool extensions and RWA registry interact correctly under load

Strategic outcome:  The core product promise is demonstrable: illiquid RWA holders receive BLD stablecoin instantly.

### M6 · Wks 12–13  —  Issuer Onboarding Platform Complete

RWA issuers apply, are vetted, pay fees, and launch markets through a self-serve platform integrated with on-chain registry logic.

- Issuer application workflow — guided entity and asset documentation with eligibility pre-checks

- On-chain fee collection — vetting and market-enabling fees without manual invoicing

- Issuer dashboard live — NAV submission, obligation calendar, market status, and compliance tracking

- Eligibility engine — real-time feedback on asset qualification against protocol rules

- Audit obligation tracker — quarterly reporting requirements visible and enforceable

Strategic outcome:  Partner onboarding scales without proportional operational headcount.

### M7 · Wks 14–15  —  Data & Analytics Platform Live

Protocol data — markets, BLD reserves, settlements, governance — is exposed via APIs and operational dashboards.

- GraphQL API live — unified query surface for markets, registry, and settlement state

- REST API complete — issuer and asset-manager operations fully covered

- Protocol analytics dashboard — BLD reserve health, swap volume, active markets, settlement queue depth

- Public transparency endpoint — on-chain and indexed data for holders and researchers

- Partner documentation published — OpenAPI and GraphQL Playground for integrators

Strategic outcome:  Institutional stakeholders, issuers, and developers access consistent, auditable protocol data.

### M8 · Wk 16  —  Full Integration & Pre-Audit Hardening

All layers — extended APSS contracts, RWA modules, backend, and frontend — are integrated, security-tested, and ready for external audit.

- End-to-end testnet validation — issuer onboarding through holder exit and settlement completion

- Penetration test completed — external red team on all public surfaces

- Static analysis clean — zero high or critical findings across smart contract scope

- Attack scenario suite complete — flash-loan, governance, and oracle manipulation vectors tested

- Infrastructure security baseline verified — WAF, DDoS protection, network segmentation

Strategic outcome:  The RWA migration enters audit with fewer unknowns, reducing remediation cost and timeline risk.

## Phase 3: Audit & Launch   Weeks 17–25

### M9 · Wks 17–20  —  First-Party Security Audit Complete

A tier-one firm audits the full RWA scope — APSS extensions and net-new modules. All material findings are resolved.

- Full-scope audit by Trail of Bits, Certora, or OpenZeppelin — migration path and new contracts in scope

- Critical and high findings remediated and re-verified

- Audit report published — transparent disclosure for issuers, investors, and partners

- Re-test sign-off obtained from auditing firm

- Protocol listed in recognised security registries where applicable

Strategic outcome:  Institutional partners receive the security assurance required before allocating RWA capital.

### M10 · Wks 21–23  —  Public Security Competition Closed

Independent researchers stress-test the RWA migration under competitive review. Valid findings are remediated before launch.

- Code4rena or Sherlock competition completed — broad coverage of BLD mechanics and RWA registry

- Competition findings triaged and remediated

- Targeted re-audit of modified modules completed

- Results published publicly

- Immunefi bug bounty configured for mainnet launch

Strategic outcome:  Community-scale review complements the firm audit. Confidence is earned, not asserted.

### M11 · Wk 24  —  Production Readiness Verified

Load, disaster recovery, and operational runbooks are validated. The RWA system meets launch-grade reliability targets.

- Load test passed — 10x projected peak swap volume without degradation

- Disaster recovery drill completed — oracle failure, database outage, and RPC loss recovered cleanly

- BLD peg monitoring and alerting live — anomalies surfaced within seconds

- On-call runbooks tested — incident response executable by any qualified engineer

- Zero-downtime upgrade pipeline validated — contract migrations deploy safely

Strategic outcome:  Real capital enters a system proven under operational stress, not best-case conditions.

### M12 · Wk 25  —  RWA Markets Live on Mainnet

The RWA architecture goes live. Existing BLD stablecoin and extended liquidity pool support instant exits for listed RWAs.

- RWA contract upgrades deployed from audited commit hash — APSS baseline preserved where unchanged

- Multi-sig ownership confirmed — no single key controls protocol functions

- First RWA markets enabled — issuer partners live at launch

- BLD liquidity maintained — stablecoin and pool extensions operational for instant exits

- Immunefi bug bounty live — continuous post-launch security coverage

- Launch communications distributed — partners, community, and public announcement

Strategic outcome:  BOUND delivers on its mission: institutional RWA liquidity on-chain, built on a deployed BLD and pool foundation.

# Development Budget

Fixed $320,000 development allocation through Milestone 12 (RWA markets live on mainnet), built on deployed APSS infrastructure. Covers engineering, infrastructure, and launch execution — audit and competition fees excluded.

| Total budget | Timeline | Team size |
| --- | --- | --- |
| $320,000 | 22 weeks | ~3.5 FTE blended team |

## Budget by Workstream

| Workstream | Amount | Milestones | Scope |
| --- | --- | --- | --- |
| Smart contracts | $90,000 | M1–M2, M8 | APSS contract extensions, RWA registry, liquidity pool upgrade path, governance alignment, migration scripts, unit and integration tests |
| Backend & oracle automation | $62,000 | M4, M7 | NAV feed integration, haircut engine, background settlement processor, issuer obligation tracker, core REST endpoints |
| Frontend & product UI | $52,000 | M3, M5, M6 | Instant exit swap interface, wallet flows, settlement tracker, issuer onboarding surfaces, protocol analytics views |
| DevOps & infrastructure | $28,000 | M3, M11 | Cloud environments, CI/CD, RPC and indexing, observability, staging and production pipelines, deployment automation |
| Architecture & program management | $32,000 | M1–M12 | APSS migration specification, technical leadership, sprint coordination, delivery governance across all phases |
| QA & integration testing | $18,000 | M5, M8, M11 | End-to-end testnet validation, regression suite, pre-mainnet integration checks, launch readiness verification |
| Mainnet launch engineering | $26,000 | M11–M12 | Contract upgrade deployment, multi-sig handover support, first-market enablement, launch runbooks and cutover execution |
| Contingency reserve | $12,000 | All phases | Buffer for APSS migration surprises, oracle integration rework, and scope adjustments within the fixed budget |

## Workforce Allocation

| Role | Duration | Amount |
| --- | --- | --- |
| Senior smart contract engineer | 18 weeks · full-time | $81,000 |
| Backend / oracle engineer | 16 weeks · full-time | $56,000 |
| Frontend engineer | 14 weeks · full-time | $45,500 |
| DevOps engineer | 8 weeks · fractional | $24,000 |
| Protocol architect / PM | 12 weeks · fractional | $36,000 |
| QA engineer | 8 weeks · fractional | $16,000 |
| Infrastructure & tooling | 22 weeks · ongoing | $28,000 |
| Integration & launch overhead | Weeks 17–22 | $21,500 |
| Contingency reserve | All phases | $12,000 |

## Budget by Phase

| Phase | Weeks | Amount | Share |
| --- | --- | --- | --- |
| Phase 1 — Foundation | Weeks 1–6 | $78,000 | 24% |
| Phase 2 — Build | Weeks 7–16 | $154,000 | 48% |
| Phase 3 — Launch | Weeks 17–22 | $88,000 | 28% |

## Excluded from Development Budget

The following are tracked and budgeted separately from the $320,000 development allocation:

- External smart contract audit (Trail of Bits, Certora, OpenZeppelin, etc.)

- Public security competition (Code4rena, Sherlock)

- Targeted re-audit fees after competition findings

- Immunefi bug bounty capital and escrow

- Legal and securities compliance advisory

© BOUND Protocol — Institutional Liquidity Infrastructure